🔍 Boyd Orr Burndown — Hackathon Build Plan

5 People · 6 Hours · Static-Site Mystery Engine

IMPORTANT

Hours 0:00–0:30 are sacred. Everyone locks in and signs off the data.json contract together before a single line of code is written. This is the interface that decouples all five workstreams.

Team Split

| Person | Role | Hours |
| --- | --- | --- |
| A | Data wrangler — ingest, clean, alias lists | 0:00 → 3:30 |
| B | Analysis — lectures, rule checks | 1:00 → 5:00 |
| C | LLM claims, graph & scoring → data.json builder | 1:30 → 5:30 |
| D | Map, story mode & speaking card | 2:00 → 6:00 |
| E | Summary screen, timeline, network graph, design & pitch | 2:00 → 6:00 |

Hour-by-Hour Timeline

Hour  0:00 ━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━ 6:00

│

All  ●──[0:00–0:30 Kickoff: agree data.json schema]──●

│

A   ●────────[ingest.py + alias lists + stays table]────●  (done ~3:30)

│                                                    │

B             ●────[lectures.py + rules.py]─────────────●  (done ~5:00)

│          depends on A's clean CSV by H1:30        │

C                  ●──[claims.py → LLM + cache]──●

│                   ●──[graph.py + scoring]──────────●

│                   ●──[build.py → data.json]────────●  (done ~5:30)

D                            ●──[map.js + story.js]──────●  (done ~6:00)

E                            ●──[summary + timeline + network + CSS]──●

│

└─────────────────────[5:30–6:00 Integration + Rehearsal]

Per-Person Task Cards

👤 Person A — Data Wrangler

Owns: pipeline/ingest.py, data/raw/extra_places.csv

| Task | Output |
| --- | --- |
| Parse 0338–0716 → start/end minutes | clean stays table |
| Parse {55.87 -4.29} → lat/lng floats | clean buildings table |
| Parse societies text → Python list | clean students table |
| Build subject alias dict (Computing Science = Computer Science) | aliases.py constants |
| Build building alias dict | aliases.py constants |
| Write extra_places.csv for Kelvingrove, QMU, etc. | hand-written CSV |
| Print unmatched names as warnings | terminal output |

Handoff to B+C by hour 1:30: clean DataFrames, alias constants, all CSVs normalised.

👤 Person B — Rules Engine

Owns: pipeline/lectures.py, pipeline/rules.py

| Task | Output |
| --- | --- |
| Regex-extract lecture windows from building descriptions | lectures table: building, subject, start, end |
| Rule: Out-of-hours stay | flag OOH with severity |
| Rule: Night presence (00:00–06:00 anywhere) | flag NIGHT |
| Rule: Lecture miss/wrong location | flag LECTURE |
| Rule: Teleport (overlap or gap too small to walk) | flag TELEPORT |
| Rule: Identity (name mismatch or unknown ID) | flag IDENTITY |

Depends on: A's clean tables (hour 1:30).
Hands off to C by hour 4:00: flag table keyed by student ID.

👤 Person C — LLM, Graph & Builder

Owns: pipeline/claims.py, pipeline/graph.py, pipeline/build.py

| Task | Output |
| --- | --- |
| Send each testimony to Claude/OpenAI with fixed JSON schema | claims table: place, time, activity, society |
| Cache every result to disk immediately | data/llm_cache/*.json |
| Rule: Testimony cross-check (claim↔stay mismatch, bad society) | flag TESTIMONY |
| Build co-presence graph (NetworkX): link if overlap ≥ N min, weight by crowd | edges list |
| Score 0–10 per student from combined flags | score field |
| Identify kingpin: clean score, highest weighted degree | kingpin key |
| Write top findings as plain sentences | findings list |
| build.py assembles web/data.json | the contract file |

Depends on: A's tables (1:30), B's flags (4:00).
Final output: web/data.json by hour 5:30 at the latest.

👤 Person D — Map & Story

Owns: web/map.js, web/story.js, web/speech.js

| Task | Output |
| --- | --- |
| Leaflet map with Carto tiles | base map layer |
| Plot buildings as polygons; flagged students as animated markers | map layer |
| Clean students faint; "show everyone" toggle | toggle UI |
| Story mode: "Play the case" steps through findings[] | fly-to + clock jump + caption |
| Speaking card: testimony vs logs side-by-side, read aloud via speechSynthesis | modal component |
| Test speech on demo laptop, keep text visible | hardened UX |

Depends on: data.json contract (agreed at hour 0:30). Can mock data until 5:30.

👤 Person E — Summary, Visuals & Pitch

Owns: web/index.html, web/app.js, web/timeline.js, web/network.js, web/style.css

| Task | Output |
| --- | --- |
| Case summary screen: suspect count, kingpin name, top 3 findings | landing page |
| Shared state object: { currentTime, selectedStudent, mode } | app.js |
| D3 swimlane timeline: one lane per student, colour-coded flag bars | timeline.js |
| D3 force graph: kingpin centred, edge weight = link thickness | network.js |
| Reveal button: clean students fade, links converge to kingpin node, name appears | dramatic finale |
| Design system: colours, fonts, mobile-safe layout | style.css |
| Pitch deck / README screenshots | presentation |

Depends on: data.json contract (hour 0:30). Can mock data until 5:30.

The data.json Contract (agree by hour 0:30)

json

{

"meta": { "generated": "ISO timestamp", "version": 1 },

"buildings": [

{ "name": "Boyd Orr", "lat": 55.872, "lng": -4.291,

"opens": 480, "closes": 1320,

"lectures": [{ "subject": "Computing Science", "start": 600, "end": 720 }] }

],

"students": [

{

"id": "S001", "name": "Alice", "age": 20, "sex": "F",

"year": 2, "subject": "Computing Science",

"height": 165, "hair": "#3d2b1f",

"societies": ["Chess Club", "Film Society"],

"score": 7.4,

"flags": [

{ "rule": "TELEPORT", "severity": "high",

"detail": "Gap of 4 min between QMU and Boyd Orr (1.2 km)" }

],

"stays": [{ "place": "Boyd Orr", "start": 590, "end": 730 }],

"claims": [{ "place": "Boyd Orr", "start": 600, "end": 720,

"activity": "lecture", "society": null }]

}

],

"edges": [

{ "a": "S001", "b": "S007", "weight": 0.83,

"overlap_min": 55, "place": "Kelvingrove Park" }

],

"findings": [

{ "rank": 1, "text": "S001 and S007 were in Kelvingrove Park together from 03:38 to 05:33.",

"time_start": 218, "time_end": 333, "place": "Kelvingrove Park",

"students": ["S001", "S007"] }

],

"kingpin": "S007"

}

Offline / Risk Mitigations

| Risk | Fix |
| --- | --- |
| Name mismatches between files | A prints all unmatched strings to terminal; fix alias dict |
| LLM API unavailable at venue | C caches every response to data/llm_cache/; re-run reads cache |
| Crowded lecture halls link everyone | Weight by 1 / occupancy; ignore pure-lecture overlaps |
| No wifi at venue | Pre-built data.json committed; Carto tiles have free offline mode; SVG fallback map |
| Speech voice differs by device | Test on demo laptop Friday night; text always visible |
| Integration chaos in last 30 min | D and E work against mock data.json all day; swap real file at 5:30 |

Folder Layout

/data

/raw          ← original CSVs, testimonies

/llm_cache    ← one JSON file per testimony (C writes, never deletes)

extra_places.csv

/pipeline

aliases.py    ← shared constants (A writes first)

ingest.py     ← A

lectures.py   ← B

rules.py      ← B

claims.py     ← C

graph.py      ← C

build.py      ← C  →  writes web/data.json

/web

index.html

app.js        ← shared state, routing

map.js        ← D

story.js      ← D

speech.js     ← D

timeline.js   ← E

network.js    ← E

style.css     ← E

data.json     ← generated by build.py

README.md

Hour-by-Hour Checkpoints

| Time | Checkpoint |
| --- | --- |
| 0:30 | ✅ data.json schema signed off, mock file committed |
| 1:30 | ✅ A hands off clean DataFrames + aliases to B and C |
| 3:30 | ✅ B has lecture table; first flags running |
| 4:30 | ✅ C has LLM claims cached; graph building |
| 5:00 | ✅ B flags done; C merges and starts build.py |
| 5:30 | ✅ Real data.json committed; D+E swap in real data |
| 5:45 | ✅ Full demo walkthrough on demo laptop |
| 6:00 | 🎬 Presentation / recording |

TIP

Biggest productivity win: D and E should never be blocked. The mock data.json (with 3–4 fake students and findings) lets them build and style everything independently for 3+ hours. The real file is a drop-in replacement.